## Лист1
Task | Start Hours | HOURS Spent-Day5 | HOURS Spent-Day4 | HOURS Spent-Day3 | HOURS Spent-Day2 | HOURS Spent-Day1 | Total Hours
Task1 | 7 | 2 | 0 | 0 | 3 | 2 | 7
Task2 | 7 | 2 | 0 | 0 | 4 | 1 | 7
Task3 | 4 | 4 | 0 | 0 | 0 | 0 | 4
Task4 | 5 | 1 | 0 | 0 | 2 | 2 | 5
Task5 | 7 | 3 | 0 | 0 | 2 | 2 | 7
Task6 | 7 | 5 | 0 | 0 | 1 | 1 | 7
Task7 | 5 | 2 | 0 | 0 | 2 | 1 | 5
Formula |  | B11-SUM(C2:C8)
Actual Remaining Hours | 42 | 23 | 24 | 24 | 10 | 0
Estimated Reaminig Hours | 42 | 33.6 | 25.2 | 16.8 | 8.4 | 0
Formula |  | B12-(B12/5)
Number of Participants | Number of Hours that participant can take part during sprint | Number of Hours ot the Team for the sprint
3 | 14 | 42
New team Focus-factor |  | 0.7
29.4

## Лист2
Number of Participants